## Aug 2022
WORK ORDER FOR PROVIDING EMPLOYMENT TO THOSE HOUSE HOLDS ISSUED JOB CARDS WHO ARE DEMANDING EMPLOYMENT UNDER MGNREGA IN MIZORAM ( AUGUST - 2022-2023 )
NAME OF DISTRICT : KHAWZAWL |  |  |  |  | Work Start Date : 29.8.2022
NAME OF BLOCK : KHAWZAWL RD |  |  |  |  | Work End date : 2.9.2022
Sl. No. | Name of Village | No. of Working Days | No.of Regis-tered Family | Name of work (please specify work for unskilled, semi-skilled and skilled Labour) | Unskilled Labour | Rate per day (Rs) | Unskilled Amount (Rs) | TOTAL (Rs) | Work Code | Measurement of work in metre per Beneficiary |  |  | Work execu-ting agen-cy
[10 empty] | Length (in metre) | Breadth (in metre) | Height (in metre)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | AIDUZAWL | 5 | 75 | Constn of Cement Concrete road Anganwadi - Playfield. Aiduzawl | 375 | 233 | 87375 | 87375 | RC/GIS/18996 | 25 | 3.5 | 0.12 | VEC
2 | ARRO | 5 | 48 | Constn of Dugout pond Lalhriatpui huan. JC.No-37 GIS arro | 240 | 233 | 55920 | 55920 | IF/GIS/18995 | 13 | 10 | 2 | VEC
3 | BIATE | 5 | 179 | Roadside plantation Tea factory to zero Point | 895 | 233 | 208535 | 208535 | DP/GIS/18992 | 205 nos. |  |  | VEC
|  | 5 | 179 | Along the cost Afforestation using forestry trees for community Hriangngaw | 895 | 233 | 208535 | 208535 | DP/GIS/18993 | 108 nos. |  |  | VEC
|  | 5 | 180 | Construction of Community Farm Pond at Vawrhkawn Zau | 900 | 233 | 209700 | 209700 | WC/GIS/18994 | 20 | 20 | 2 | VEC
4 | CHALRANG | 5 | 163 | Drainage of community water logged land near communityn hall at chalrang GIS chalrang | 815 | 233 | 189895 | 189895 | LD/GIS/18991 | 190 | 0.5 | 0.5 | VEC
5 | CHAWNGTLAI | 5 | 386 | Drainage of community waterlogged land from Phaiveng, from Pu Chhuanawma house to lane hnuai GIS Chawngtlai | 1930 | 233 | 449690 | 449690 | LD/GIS/1899 | 440 | 0.5 | 0.5 | VEC
6 | CHHAWRTUI | 5 | 245 | Drainage of community water-logged land for Community at Chhawrtui tuikhur to main road (On going). Chhawrtui | 1225 | 233 | 285425 | 285425 | IF/GIS/18989 | 280 | 0.5 | 0.5 | VEC
7 | DULTE | 5 | 222 | Constn.of continous Contour trench at Tuitai. Dulte | 1110 | 233 | 258630 | 258630 | IF/GIS/18988 | 515 nos. |  |  | VEC
8 | HMUNCHENG | 5 | 91 | Constn.of Individual Farmpond at Lalchhanchuaha huan,serzawl jc.no-39 GIS hmuncheng | 455 | 233 | 106015 | 106015 | IF/GIS/18987 | 15 | 14 | 2 | VEC
9 | KAWLKULH | 5 | 528 | Constn of Cement Concrete road at Thlanmual No II. Kawlkulh | 2640 | 233 | 615120 | 615120 | RC/GIS/18986 | 198 | 3.1 | 0.15 | VEC
10 | KHAWHAI | 5 | 187 | Constn.of mini percolation tank for individual Lalremruati sailo huan,JC No-592 GIS Khawhai | 935 | 233 | 217855 | 217855 | IF/GIS/18983 | 21 | 20 | 2 | VEC
|  | 5 | 187 | Constn.of mini percolation tank for individual Lianchungnunga huan,JC No-392 GIS Khawhai | 935 | 233 | 217855 | 217855 | IF/GIS/18997 | 21 | 20 | 2 | VEC
|  | 5 | 187 | Constn.of mini percolation tank for individual lalthangkima huan,JC No-465 GIS Khawhai | 935 | 233 | 217855 | 217855 | IF/GIS/18985 | 21 | 20 | 2 | VEC
11 | KHAWZAWL I | 5 | 122 | Constn of individual farmpond at Thangpuii huan JC.No-821 GIS Kzl-I | 610 | 233 | 142130 | 142130 | IF/GIS/18981 | 18 | 15 | 2 | VEC
|  | 5 | 123 | Constn of individual farmpond at B.Lalhriatpuii huan JC.No-922 GIS Kzl-I | 615 | 233 | 143295 | 143295 | IF/GIS/18982 | 18 | 15 | 2 | VEC
12 | KHAWZAWL II | 5 | 585 | Constn of irrigation open well for Community at vengthar Field. | 2925 | 233 | 681525 | 681525 | IC/GIS/18980 | 25 | 20 | 5 | VEC
13 | KHAWZAWL III | 5 | 263 | Wasteland Block Plantation of Farm Forestry Trees at tuisen Phai zau. Khawzawl -III | 1315 | 233 | 306395 | 306395 | DP/GIS/18979 | 300 nos |  |  | VEC | 263
14 | KHAWZAWL IV | 5 | 294 | Constn.of Piggery Shelter at Hunnghakliana huan halsual.Khawzawl -IV | 1470 | 233 | 342510 | 342510 | AV/GIS/18977 | 33 | 20 |  | VEC
15 | KHAWZAWL V | 5 | 311 | Constn of cement concrete Road for Community at Lalnienga’s House to JNV Road (On going). Khawzawl -V | 1555 | 233 | 362315 | 362315 | RC/GIS/18976 | 135 | 3 | 0.15 | VEC
16 | KHUALEN | 5 | 51 | Constn of Soakage Channel for Community at vengchhak. Khualen | 255 | 233 | 59415 | 59415 | IF/GIS/18975 | 12 | 10 | 2 | VEC
17 | LUNGTAN | 5 | 131 | Constn of Water tank at PC Hrangzuala huan J/C No-12 GIS Lungtan | 655 | 233 | 152615 | 152615 | IF/GIS/18974 | 20 | 15 | 2 | VEC
18 | NGAIZAWL | 5 | 195 | Constn.of gravel road from Chin Suan Dal in to Nang Deih Mung in GIS ngaizawl(on going) | 975 | 233 | 227175 | 227175 | RC/GIS/18973 | 128 | 3.5 | 0.15 | VEC
19 | NEIHDAWN | 5 | 142 | Constn of Cement Concrete road from Biakzama house to dumping ground. Neihdawn | 710 | 233 | 165430 | 165430 | RC/GIS/18972 | 75 | 3 | 0.15 | VEC
20 | N.CHALRANG | 5 | 141 | Maintenance of cement concrete road for community at kawn field GIS N.chalrang | 705 | 233 | 164265 | 164265 | RC/GIS/18971 | 75 | 3 | 0.15 | VEC
21 | PAMCHUNG | 5 | 83 | Constn of Gravel road from Pamchung to Tuiphal. Pamchung | 415 | 233 | 96695 | 96695 | RC/GIS/18970 | 120 | 3.5 | 2 | VEC
22 | PUILO | 5 | 113 | Constn of Dugout pond for K. Lalremruata . Puilo | 565 | 233 | 131645 | 131645 | IF/GIS/18969 | 18 | 14 | 2 | VEC
23 | RABUNG | 5 | 169 | Constn of Farmpond for Individual at Vanlallawma. Rabung | 845 | 233 | 196885 | 196885 | IF/GIS/18967 | 20 | 19 | 2 | VEC
|  | 5 | 169 | Constn of Farmpond for Individual at Chawngchhunga Rabung | 845 | 233 | 196885 | 196885 | IF/GIS/18968 | 20 | 19 | 2 | VEC
24 | RIANGTLEI | 5 | 99 | Constn.of cement concrete road from Vanlalzami House to Lalengzama House GIS Riangtlei | 495 | 233 | 115335 | 115335 | RC/GIS/18966 | 43 | 3 | 0.15 | VEC
25 | SIALHAWK | 5 | 498 | Constn.of Community Farmpond at leisekawt GIS Sialhawk (on going) | 2490 | 233 | 580170 | 580170 | WC/GIS/18964 | 30 | 25 | 3 | VEC
26 | TLANGMAWI | 5 | 41 | Maintenance of cement concrete road from tlangmawi to sialhawk GIS Tlangmawi | 205 | 233 | 47765 | 47765 | RC/GIS/18931 | 21 | 3 | 0.15 | VEC
27 | TLANGPUI | 5 | 169 | Land Development at Ralkah Zau pineapple hmun,GIS Tlangpui | 845 | 233 | 196885 | 196885 | LD/GIS/18930 | 790 | 2 | 1 | VEC
28 | TUALPUI | 5 | 142 | Constn of Mini Percolation tank at Lalmuanthangi. Tualpui | 710 | 233 | 165430 | 165430 | WC/GIS/18929 | 20 | 14.2 | 2 | VEC
29 | TUALTE | 5 | 124 | Constn of Individual farmpond for Vanlalkima JC No-259 GIS tualte | 620 | 233 | 144460 | 144460 | IF/GIS/18927 | 20 | 14 | 2 | VEC
|  | 5 | 124 | Renovation of Primary school GIS Tualte | 620 | 233 | 144460 | 144460 | AV/GIS/18928 | 20 | 14.2 | 2 | VEC
30 | VANKAL | 5 | 101 | Constn of cement concrete road from Sasawkawn to balhla huan. Vankal | 505 | 233 | 117665 | 117665 | RC/GIS/18925 | 51 | 3.1 | 0.15 | VEC
31 | VANGTLANG | 5 | 101 | Maintenance of cement concrete road from Lalruata House to Lianhnuna House GIS Vangtlang | 505 | 233 | 117665 | 117665 | RC/GIS/18924 | 52 | 3 | 0.15 | VEC
32 | KHAWZAWL HERMON | 5 | 171 | Constn.of individual Farmpond for F.Lalchangliana jc no-269 GIS Hermon | 855 | 233 | 199215 | 199215 | IF/GIS/18922 | 20 | 19 | 2 | VEC
|  | 5 | 170 | Constn.of Dug out pond for TBC.Lalnuntluanga huan GIS hermon | 850 | 233 | 198050 | 198050 | IF/GIS/18923 | 20 | 19 | 2 | VEC
33 | KHAWZAWL KAWNZAR | 5 | 176 | Constn.of mini percolation tank for individual at Zothansiama Colney huan Jc.No-190. GIS,Kawnzar | 880 | 233 | 205040 | 205040 | IF/GIS/18921 |  |  |  | VEC
34 | KHAWZAWL LUNGVAR | 5 | 176 | Drainage of community water logged land from Khiangliana house to thlanmual peng (On going). Lungvar | 880 | 233 | 205040 | 205040 | LD/GIS/18920 | 200 | 0.5 | 0.5 | VEC
35 | KAWLKULH N | 5 | 132 | Constn. Of Contour Trench at Lalnuntluanga, KKN | 660 | 233 | 153780 | 153780 | IF/GIS/18917 | 301 nos. |  |  | VEC
|  | 5 | 133 | Constn. Of Level Bench terrace Ramngaihsangi, KKN | 665 | 233 | 154945 | 154945 | /IF/GIS/18919 | 610 | 2 | 1 | VEC
36 | VANCHENGPUI | 5 | 169 | Constn of minor irrigation Canal for community at nearBiaknema (On going). Vanchengpui | 845 | 233 | 196885 | 196885 | IC/GIS/18916 | 260 | 0.5 | 0.5 | VEC
37 | KHAWZAWL ARRO | 5 | 121 | Constn of Level Bench Terrace at T.Lalringliana Huan. Khawzawl Arro | 605 | 233 | 140965 | 140965 | IF/GIS/18915 | 570 | 2 | 1 | VEC
38 | KHAWZAWL ZAINGEN | 5 | 262 | Improvement of road approach to Zaingen hmun. Zaingen | 1310 | 233 | 305230 | 305230 | RC/GIS/18914 | 400 | 3 | 2 | VEC
|  |  | 8658 | G.TOTAL |  |  |  | 10086570
(LALTHAKIMA CHHANGTE)
Programme Officer
Mahatma Gandhi National Rural Employment Guarantee Act
Khawzawl R.D. Block
Khawzawl.