## Sheet1
WORK ORDER FOR PROVIDING EMPLOYMENT TO THOSE HOUSE HOLDS ISSUED JOB CARDS WHO ARE DEMANDING EMPLOYMENT UNDER MGNREGA IN MIZORAM (November 2023)
NAME OF DISTRICT |  |  | : | KHAWZAWL |  |  |  |  | Financial Year : 2023 - 2024
NAME OF BLOCK |  |  | : | KHAWZAWL | Work Start Date :14.11.2023 Work End Date : 27.11.2023
Sl. No. | Name of Village | No of work-ing days | No of Regis-tered Family | Name of work (please specify work for unskilled, semi-skilled and skilled Labour) | Unskilled Labour | Rate per day (Rs) | Unskilled Amount (Rs) | TOTAL | Work Code | Measurement of work in metre per benificiary |  |  | Work execu-ting agency
[10 empty] | Length (in metre) | Breadth (in metre) | Height (in metre)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | AIDUZAWL | 14 | 75 | Constn of Comunity water logged land from Anganwadi to Zawngtah kawi | 1050 | 249 | 261450 | 261450 | LD/GIS/42445 | 40 | 0.3 | 0.3 | VEC
2 | CHHAWRTUI | 14 | 251 | Constn of Boulder Checkdam for Community at Field sir | 3514 | 249 | 874986 | 874986 | WC/GIS/42447 | 40 | 1 | 4 | VEC
3 | DULTE | 14 | 231 | Constn of Compost pit for 8 families | 3234 | 249 | 805266 | 805266 | F/GIS/42448 | 2 | 1.5 | 1.5 | VEC
4 | KAWLKULH | 14 | 264 | Community Farmpond at paihte hmun. | 3696 | 249 | 920304 | 920304 | F/GIS/42449 | 6 | 4 | 2.5 | VEC
|  | 14 | 264 | Construction of Compost pit for 3 Families | 3696 | 249 | 920304 | 920304 | IF/GIS/42450 | 4 | 3 | 2 | VEC
5 | KHAWZAWL-III | 14 | 200 | Constn of Upland Bench Terrace at Khuailui zau. | 2800 | 249 | 697200 | 697200 | IF/GIS/42452 | 300 | 2 | 1 | VEC
|  | 14 | 72 | Half Moon Terrace at H.Vanlalhruaia Huan. JC.No-628. | 1008 | 249 | 250992 | 250992 | IF/GIS/42457 | 150 | 2 | 1 | VEC
6 | KHAWZAWL-IV | 14 | 296 | Constn of Cement Concrete road from Vanlalhuma house to Pu Dula tui(New) | 4144 | 249 | 1031856 | 1031856 | RC/GIS/42458 | 150 | 3 | 0.1 | VEC
7 | KHAWZAWL-V | 14 | 319 | Construction for WRC for Community | 4466 | 249 | 1112034 | 1112034 | IF/GIS/42460 | 200 | 5 | 1 | VEC
8 | KHUALEN | 14 | 53 | Construction of Cement Concrete road from Hall peng to Clinic Centre | 742 | 249 | 184758 | 184758 | RC/GIS/42462 | 30 | 3 | 0.1 | VEC
9 | NEIHDAWN | 14 | 147 | Construction of Farhuan Agriculture link road (On going) | 2058 | 249 | 512442 | 512442 | RC/GIS/42463 | 200 | 3 | 0.1 | VEC
10 | PAMCHUNG | 14 | 83 | Construction of Community Water loggedland | 1162 | 249 | 289338 | 289338 | LD/GIS/42464 | 40 | 0.3 | 0.3 | VEC
11 | PUILO | 14 | 57 | Constn of Poultry Livestock shelter for Neihkimi/C No 159 | 798 | 249 | 198702 | 198702 | IF/GIS/42466 | 4 | 2 | 2.5 | VEC
|  | 14 | 56 | Constn of Poultry Livestock shelter for Lalnunziri /C No 185 | 784 | 249 | 195216 | 195216 | IF/GIS/42469 | 4 | 2 | 2.5 | VEC
12 | RABUNG | 14 | 341 | Maintenance of Internal road from Bungveng to Bilbawk | 4774 | 249 | 1188726 | 1188726 | RC/GIS/42471 | 200 | 3 | 0.1 | VEC
13 | TUALPUI | 14 | 151 | Constn of Cement concrete road near R. Lalnunsanga (New) | 2114 | 249 | 526386 | 526386 | RC/GIS/42473 | 70 | 3 | 0.1 | VEC
14 | VANKAL | 14 | 105 | Constn of Dugout Pond at Lalthuthlunga huan | 1470 | 249 | 366030 | 366030 | IF/GIS/42475 | 15 | 5 | 1.5 | VEC
15 | KHAWZAWL LUNGVAR | 14 | 59 | Constn of piggery shelter for HP.Lalfakawma | 826 | 249 | 205674 | 205674 | IF/GIS/42477 | 5 | 2.5 | 2 | VEC
|  | 14 | 59 | Constn of piggery shelter for Biakchungnunga | 826 | 249 | 205674 | 205674 | IF/GIS/42478 | 5 | 2.5 | 2 | VEC
|  | 14 | 59 | Constn of piggery shelter for Biakchungnunga Lalthianghlimi | 826 | 249 | 205674 | 205674 | IF/GIS/42479 | 5 | 2.5 | 2 | VEC
16 | KAWLKULH NORTH | 14 | 131 | Renovation of water Bodies at Darnam Tuikhur | 1834 | 249 | 456666 | 456666 | WC/GIS/42480 | - | - | - | VEC
|  | 14 | 131 | Renovation of water Bodies at Mawt Tuikhur | 1834 | 249 | 456666 | 456666 | WC/GIS/42481 | - | - | - | VEC
17 | VANCHENGPUI | 14 | 179 | Constn of Cement concrete road at K. Lalrosanga to Lalramenga house | 2506 | 249 | 623994 | 623994 | RC/GIS/42482 | 120 | 3 | 0.1 | VEC
18 | KHAWZAWL ARRO | 14 | 61 | Constn of Piggery Shelter at Rampuia Huan (On going) | 854 | 249 | 212646 | 212646 | IF/GIS/42483 | 5 | 2.5 | 2 | VEC
|  | 14 | 61 | widening of road near R. Rinmawia house | 854 | 249 | 212646 | 212646 | RC/GIS/42484 | 100 | 1.5 | 0.1 | VEC
19 | KHAWZAWL ZAINGEN | 14 | 260 | Constn of road approach to Vengtghlang Tuikhur (New) | 3640 | 249 | 906360 | 906360 | RC/GIS/42485 | 200 | 3 | 0.1 | VEC
20 | ARRO | 14 | 49 | Constn of gravel road for community from from Arro to Khawzawl,arro | 686 | 249 | 170814 | 170814 | RC/GIS/42486 | 40 | 3 | 0.1 | VEC
21 | BIATE | 14 | 528 | Constn.of Gravel Road for Community at Dilmual zau,Biate | 7392 | 249 | 1840608 | 1840608 | RC/GIS/42488 | 2 km | 3 | 2 | VEC
22 | CHALRANG | 14 | 164 | Constn.of Gravel Road for Community at Chulhuan zau,Chalrang | 2296 | 249 | 571704 | 571704 | RC/GIS/42490 | 200 | 3 | 2 | VEC
23 | CHAWNGTLAI | 14 | 201 | Drainage of Community waterlogged land from Isaka house to Tualte Road new,chawngtlai | 2814 | 249 | 700686 | 700686 | LD/GIS/42492 | 200 | 0.3 | 0.3 | VEC
|  | 14 | 100 | Constn.of Dug Out Pond for Lalremruata huan.chawngtlai | 1400 | 249 | 348600 | 348600 | IF/GIS/42494 | 20 | 10 | 1.5 | VEC
|  | 14 | 100 | Construction of Individual Farm Pond for B.Lalfakliana huan,chawngtlai | 1400 | 249 | 348600 | 348600 | IF/GIS/42496 | 4 | 2 | 1.5 | VEC
24 | HMUNCHENG | 14 | 47 | Levelling/shaping of wasteland at H.Lalthlamuanpuia huan,Lunghmul kam jc no-102,hmuncheng | 658 | 249 | 163842 | 163842 | LD/GIS/42498 | 100 | 4 | 1 | VEC
|  | 14 | 48 | Levelling/shaping of wasteland at RK.Chhunga huan,Lunghmul kam jc no-41,hmuncheng | 672 | 249 | 167328 | 167328 | LD/GIS/42500 | 100 | 4 | 1 | VEC
25 | KHAWHAI | 14 | 540 | Maintenance of cement concrete road from Ramherliani house to Lalthanzama house,khawhai | 7560 | 249 | 1882440 | 1882440 | RC/GIS/42502 | 400 | 3 | 0.1 | VEC
26 | KHAWZAWL - I | 14 | 100 | Maintenance of cement concrete road from Biaktluangi House to Muallungthu.Kzl-I on going | 1400 | 249 | 348600 | 348600 | RC/GIS/42502 | 80 | 3 | 0.1 | VEC
|  | 14 | 100 | Drainage of community water logged land at Drain at 3rd Lane. Kzl-i | 1400 | 249 | 348600 | 348600 | LD/GIS/42500 | 150 | 0.3 | 0.3 | VEC
|  | 14 | 49 | Constn of Dug Out Pond at Khawtinlala huan. JC.No-766.kzl-i | 686 | 249 | 170814 | 170814 | IF/GIS/42499 | 20 | 10 | 1.5 | VEC
27 | KHAWZAWL - II | 14 | 100 | Development of fallow land for individual at Sangthuami JC.No-1015.kzl-II | 1400 | 249 | 348600 | 348600 | IF/GIS/42495 | 100 | 5 | 1 | VEC
|  | 14 | 100 | Development of fallow land for individual at Kapkimi JC.No-925..kzl-II | 1400 | 249 | 348600 | 348600 | IF/GIS/42493 | 100 | 5 | 1 | VEC
|  | 14 | 100 | Constn of Level benches Terrace for individual at Lalhmingmawii JC.No-714..kzl-II | 1400 | 249 | 348600 | 348600 | IF/GIS/42491 | 300 | 2 | 1 | VEC
|  | 14 | 100 | Constn of Livestock Poultry shelter for community at Kumari .kzl-II | 1400 | 249 | 348600 | 348600 | IF/GIS/42489 | 5 | 2 | 2.5 | VEC
|  | 14 | 100 | Constn of Livestock Poultry shelter for community at Khuangkimi .kzl-II | 1400 | 249 | 348600 | 348600 | IF/GIS/42487 | 5 | 2 | 2.5 | VEC
|  | 14 | 95 | Drainage water logged -land for Community at K.hmingthansanga House to Phaisen hnar on going .kzl-II | 1330 | 249 | 331170 | 331170 | LD/GIS/42475 | 100 | 1 | 1 | VEC
28 | TLANGMAWI | 14 | 43 | Maintenance of road from Tlangmawi to Phulpui tlangmawi | 602 | 249 | 149898 | 149898 | RC/GIS/42473 | 50 | 3 | 1 | VEC
29 | TLANGPUI | 14 | 100 | Constn. Of Agri. Produce Storage Building at Lungkah tlangpui | 1400 | 249 | 348600 | 348600 | AV/GIS/42472 | 5 | 3 | 2.5 | VEC
|  | 14 | 69 | Levelling of Playfield tlangpui | 966 | 249 | 240534 | 240534 | LD/GIS/42470 | 90 | 10 | 1 | VEC
30 | LUNGTAN | 14 | 132 | Constn. of cement concrete road road from Main road to Anganwadi -I new lungtan | 1848 | 249 | 460152 | 460152 | RC/GIS/42468 | 80 | 3 | 1 | VEC
31 | NGAIZAWL | 14 | 199 | Drainage of Water logged -land for Community near Hau Go Kap house (on going),ngaizawl | 2786 | 249 | 693714 | 693714 | LD/GIS/42466 | 100 | 0.4 | 0.4 | VEC
32 | N.CHALRANG | 14 | 72 | Constn of piggery shelter at C.Lalrinmawia JC No-186 n.chalrang | 1008 | 249 | 250992 | 250992 | IF/GIS/42460 | 5 | 2.5 | 2 | VEC
|  | 14 | 72 | Constn of piggery shelter at F.Chalkima JC No-57n.chalrang | 1008 | 249 | 250992 | 250992 | IF/GIS/42464 | 5 | 2.5 | 2 | VEC
33 | RIANGTLEI | 14 | 100 | Constn.of cement concrete road from Chanchinmawia House to Thlanmual riangtlei | 1400 | 249 | 348600 | 348600 | RC/GIS/42459 | 50 | 3 | 0.1 | VEC
34 | SIALHAWK | 14 | 507 | Constn.of Gravel road At Phawtun zau sialhawk | 7098 | 249 | 1767402 | 1767402 | RC/GIS/42456 | 2 km | 3 | 2 | VEC
35 | TUALTE | 14 | 250 | Community land development for Tomato hmun at rialden zau(150 families) tualte | 3500 | 249 | 871500 | 871500 | DP/GIS/42455 | 4 Ha |  |  | VEC
36 | VANGTLANG | 14 | 102 | Constn.of gravel road at Thingthupui. Vangtlang | 1428 | 249 | 355572 | 355572 | RC/GIS/42454 | 150 | 3 | 2 | VEC
37 | KHAWZAWL HERMON | 14 | 42 | Const'n of boulder checkdam for community at Phaisen zau,hermon on going hermon | 588 | 249 | 146412 | 146412 | WC/GIS/42452 | 20 | 1 | 2 | VEC
|  | 14 | 300 | Maintenance of cement concrete road from Lalchhuanmawia in to Vety Dept peng hermon | 4200 | 249 | 1045800 | 1045800 | RC/GIS/42451 | 300 | 3 | 0.1 | VEC
38 | KHAWZAWL KAWNZAR | 14 | 193 | Maintenance of cement concrete road from Tuikhur to R. Thangliana House kawnzar | 2702 | 249 | 672798 | 672798 | RC/GIS/42446 | 100 | 3 | 0.1 | VEC
G.TOTAL |  |  | 8767 |  |  |  |  | 30561762
(LALTHAKIMA CHHANGTE)
Programme Officer
Mahatma Gandhi National Rural Employment Guarantee Act
Khawzawl R.D. Block
Khawzawl.