## Sheet1
WORK ORDER FOR PROVIDING EMPLOYMENT TO THOSE HOUSE HOLDS ISSUED JOB CARDS WHO ARE DEMANDING EMPLOYMENT UNDER MGNREGA IN MIZORAM (JUNE, 2024)
NAME OF DISTRICT |  |  | : | KHAWZAWL |  |  |  |  | Financial Year : 2024 - 2025
NAME OF BLOCK |  |  | : | KHAWZAWL | Work Start Date 18.6.2024 Work End Date 28.6.2024
Sl. No. | Name of Village | No of work-ing days | No of Regis-tered Family | Name of work (please specify work for unskilled, semi-skilled and skilled Labour) | Unsk-illed Labour | Rate per day (Rs) | Unskilled Amount (Rs) | TOTAL | Work Code | Measurement of work in metre per benificiary |  |  | Work execu-ting agency
[10 empty] | Length (in metre) | Breadth (in metre) | Height (in metre)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | AIDUZAWL | 10 | 60 | Constn.of Gravel Road for community at Zotui mual.Aiduzawl | 600 | 266 | 159600 | 159600 | 2206002001/RC/38380 | 160 | 3.5 | 2 | VEC
|  | 10 | 14 | Constn.of Gravel Road for community at Zotui mual.Aiduzawl | 140 | 266 | 37240 | 37240 | 2206002001/RC/38418 | 39 | 3.5 | 2 | VEC
2 | CHHAWRTUI | 10 | 183 | Constn of Link road at Khawihruhlian kawng | 1830 | 266 | 486780 | 486780 | 2206002006/RC/38382 | 1190 | 3.5 | 2 | VEC
|  | 10 | 70 | Levelling / shaping of wasteland for individual at PC.Zodinsangi, | 700 | 266 | 186200 | 186200 | 2206002006/IF/68945 | 128 | 10 | 0.5 | VEC
3 | DULTE | 10 | 150 | Maintenance of Gravel road at Chhimluang | 1500 | 266 | 399000 | 399000 | 2206002008/RC/38384 | 410 | 3.5 | 2 | VEC
|  | 10 | 67 | Constn of Dugout pond at Thangdawla, Dulte , Kzl | 670 | 266 | 178220 | 178220 | 2206002008/IF/68949 | 18 | 17 | 2 | VEC
4 | KAWLKULH | 10 | 183 | Maintenance of Gravel road Vanchhawng ram | 1830 | 266 | 486780 | 486780 | 2206002010/RC/38385 | 840 | 2 | 2 | VEC
|  | 10 | 172 | Road side tree plantation for community from Bangla kawn to Darkhuang | 1720 | 266 | 457520 | 457520 | 2206002010/DP/8791 | 163 nos. |  |  | VEC
|  | 10 | 71 | Constn.of Dug Out Pond for individual at Lalchhanpuia | 710 | 266 | 188860 | 188860 | 2206002010/IF/68955 | 18 | 17 | 2 | VEC
|  | 10 | 70 | Constn.of Dug Out Pond for individual at R.Lalngaihzuali | 700 | 266 | 186200 | 186200 | 2206002010/IF/68957 | 18 | 17 | 2 | VEC
5 | KHAWZAWL-III | 10 | 50 | Constn.of Level bench terrace at Ngurkhumi, Kzl-III, Kzl | 500 | 266 | 133000 | 133000 | 2206002015/IF/68961 | 460 | 2 | 1 | VEC
|  | 10 | 50 | Constn.of Level bench terrace at PC Thlamuana, Kzl-III, Kzl | 500 | 266 | 133000 | 133000 | 2206002015/IF/68962 | 460 | 2 | 1 | VEC
|  | 10 | 122 | Development for fallow land for Individual at Lalnunmawii huan. | 1220 | 266 | 324520 | 324520 | 2206002015/IF/68969 | 100 | 18 | 0.5 | VEC
|  | 10 | 50 | Constn.of Level bench terrace at PC, Dothuama, Kzl-III, Kzl | 500 | 266 | 133000 | 133000 | 2206002015/IF/68973 | 660 | 2 | 1 | VEC
6 | KHAWZAWL-IV | 10 | 85 | Constn.of Water courses for comminuty at C. Lianhnuni, Kzl-IV, Kzl | 850 | 266 | 226100 | 226100 | 2206002016/IF/68977 | 150 | 10 | 0.5 | VEC
|  | 10 | 84 | Constn.of Dugout pond at Tlangchhanthanga, Kzl-IV, Kzl | 840 | 266 | 223440 | 223440 | 2206002016/IF/68980 | 20 | 19 | 2 | VEC
|  | 10 | 60 | Constn.of Level bench terrace at K. Biakthuami, Kzl-IV, Kzl | 600 | 266 | 159600 | 159600 | 2206002016/IF/68982 | 550 | 2 | 1 | VEC
|  | 10 | 60 | Constn.of Level bench terrace at Chawngliani, Kzl-IV, Kzl | 600 | 266 | 159600 | 159600 | 2206002016/IF/68983 | 550 | 2 | 1 | VEC
7 | KHAWZAWL-V | 10 | 80 | Constn of Dugout pond at PC Laltanpuia, Kzl-V, Kzl | 800 | 266 | 212800 | 212800 | 2206002017/IF/68986 | 20 | 20 | 1.8 | VEC
|  | 10 | 80 | Constn of Dugout pond at Vanlalthanga, Kzl-V, Kzl | 800 | 266 | 212800 | 212800 | 2206002017/IF/68989 | 20 | 20 | 1.8 | VEC
|  | 10 | 81 | Constn of Dugout pond atRamchhantluanga, Kzl-V, Kzl | 810 | 266 | 215460 | 215460 | 2206002017/IF/68991 | 20 | 20 | 1.8 | VEC
|  | 10 | 81 | Constn of Dugout pond at HD Lalramthara, Kzl-V, Kzl | 810 | 266 | 215460 | 215460 | 2206002017/IF/68994 | 20 | 20 | 1.8 | VEC
8 | KHUALEN | 10 | 52 | Drainage of Water logged -land for Community from Playground to kawngpui | 520 | 266 | 138320 | 138320 | 2206002018/IC/3375 | 42 | 1 | 1 | VEC
9 | NEIHDAWN | 10 | 144 | Renovation .of community water harvesting ponds at Sikul tlang, Neihdawn, Kzl(On going) | 1440 | 266 | 383040 | 383040 | 2206002023/WC/15140 |  |  |  | VEC
10 | PAMCHUNG | 10 | 78 | Maintenance of Gravel road at Saihum kawng | 780 | 266 | 207480 | 207480 | 2206002025/RC/38386 | 226 | 3.5 | 1.8 | VEC
11 | PUILO | 10 | 124 | Afforestation for community at Puilo Ram | 1240 | 266 | 329840 | 329840 | 2206002026/DP/8795 | 500 nos. |  |  | VEC
12 | RABUNG | 10 | 183 | Constn.of Gravel Road for community from Chawlhhmun to Kangchhia | 1830 | 266 | 486780 | 486780 | 2206002027/RC/38387 | 558 | 4 | 1.5 | VEC
|  | 10 | 78 | Constn of Individual terrace atK, saithuama huan, Rabung Kzl | 780 | 266 | 207480 | 207480 | 2206002027/IF/69102 | 700 | 2 | 1 | VEC
|  | 10 | 78 | Constn of Individual terrace at C. Liansanga huan, Rabung Kzl | 780 | 266 | 207480 | 207480 | 2206002027/IF/69103 | 700 | 2 | 1 | VEC
13 | TUALPUI | 10 | 50 | Constn.of contour trench for individual at R.Lalngaihawma huan | 500 | 266 | 133000 | 133000 | 2206002032/IF/69104 | 228 nos. |  |  | VEC
|  | 10 | 50 | Constn of Individual terrace at R. Vanlalzama | 500 | 266 | 133000 | 133000 | 2206002032/IF/69105 | 460 | 2 | 1 | VEC
|  | 10 | 50 | Constn of Individual terrace at V. Zamthanga huan | 500 | 266 | 133000 | 133000 | 2206002032/IF/69106 | 460 | 2 | 1 | VEC
14 | VANKAL | 10 | 104 | Constn of Dugout pond for individual at lalrintluanga, Vankal, kzl | 1040 | 266 | 276640 | 276640 | 2206002035/IF/69107 | 23 | 20 | 2 | VEC
15 | KHAWZAWL LUNGVAR | 10 | 85 | Constn of Dugout pond Biakchhungnunga, Lungvar, Kzl | 850 | 266 | 226100 | 226100 | 2206002040/IF/69108 | 20 | 20 | 1.8 | VEC
|  | 10 | 86 | Constn of Dugout pond Lalremsangpuii, Lungvar, Kzl | 860 | 266 | 228760 | 228760 | 2206002040/IF/69109 | 20 | 20 | 1.8 | VEC
16 | KAWLKULH NORTH | 10 | 77 | Constn.of halfmoon level bench terrace for individual at R.Bialzauava huan | 770 | 266 | 204820 | 204820 | 2206002042/IF/69114 | 700 nos. |  |  | VEC
|  | 10 | 77 | Constn of level benchTerrace for individual at R. Lalthlengliana | 770 | 266 | 204820 | 204820 | 2206002042/IF/69115 | 700 | 2 | 1 | VEC
|  | 10 | 34 | Constn.of NADEP Compost structure for individual at Zoramnghaka ,KKN, Kzl | 340 | 266 | 90440 | 90440 | 2206002042/IF/69117 | 3 | 2 | 1.5 | VEC
|  | 10 | 77 | Constn of level benchTerrace for individual at Ngursangpuii sailo,KKN Kzl | 770 | 266 | 204820 | 204820 | 2206002042/IF/69116 | 700 | 2 | 1 | VEC
17 | VANCHENGPUI | 10 | 86 | Constn of Dugout pond for individual at Lalliansanga ,Vchp, Kzl | 860 | 266 | 228760 | 228760 | 2207001029/IF/69110 | 20 | 19 | 2 | VEC
|  | 10 | 86 | Constn of Dugout pond for individual at Vanlalhuma ,Vchp, Kzl | 860 | 266 | 228760 | 228760 | 2207001029/IF/69111 | 20 | 19 | 2 | VEC
18 | KHAWZAWL ARRO | 10 | 80 | Constn of Dugout pond for Zachangi huan, Kzl arro, kzl | 800 | 266 | 212800 | 212800 | 2206002043/IF/69112 | 20 | 18 | 2 | VEC
|  | 10 | 34 | Constn.of NADEP Compost structure for individual at Remthanga huan | 340 | 266 | 90440 | 90440 | 2206002043/IF/69113 | 3 | 2 | 1.5 | VEC
19 | KHAWZAWL ZAINGEN | 10 | 71 | Constn of Level bench terrace for individual at JH Kaptluanga, Zaingen, Kzl | 710 | 266 | 188860 | 188860 | 2206002044/IF/69118 | 640 | 2 | 1 | VEC
|  | 10 | 71 | Constn of Level bench terrace for individual at JH Lalnunmawia, Zaingen, Kzl | 710 | 266 | 188860 | 188860 | 2206002044/IF/69119 | 640 | 2 | 1 | VEC
|  | 10 | 71 | Constn of Level bench terrace for individual at Rochhari, Zaingen, Kzl | 710 | 266 | 188860 | 188860 | 2206002044/IF/69120 | 640 | 2 | 1 | VEC
|  | 10 | 34 | Constn.of NADEP Pit at Ronihtlinga huan | 340 | 266 | 90440 | 90440 | 2206002044/IF/69121 | 3 | 2 | 1.5 | VEC
20 | ARRO | 10 | 44 | Constn ofLevel Bench Terrace for individual at Zathluaii huan. JC.No-74 | 440 | 266 | 117040 | 117040 | 2206002002/IF/69101 | 400 | 2 | 1 | VEC
21 | BIATE | 10 | 85 | Constn.of level bench terrace for individual at TBC.Vanlalmawia huan Biate | 850 | 266 | 226100 | 226100 | 2206002003/IF/68870 | 304 | 2 | 1 | VEC
|  | 10 | 85 | Constn.of level bench terrace for individual at R.Lalremsanga huan Biate | 850 | 266 | 226100 | 226100 | 2206002003/IF/68875 | 304 | 2 | 1 | VEC
|  | 10 | 85 | Constn.of level bench terrace for individual at Lalfakmawia Ralte huan Biate | 850 | 266 | 226100 | 226100 | 2206002003/IF/68878 | 304 | 2 | 1 | VEC
|  | 10 | 86 | Constn.of level bench terrace for individual at Lalrosema huan Biate | 860 | 266 | 228760 | 228760 | 2206002003/IF/68884 | 304 | 2 | 1 | VEC
|  | 10 | 86 | Constn.of level bench terrace for individual at B.Lalremzuala huan Biate | 860 | 266 | 228760 | 228760 | 2206002003/IF/68886 | 304 | 2 | 1 | VEC
|  | 10 | 86 | Constn.of level bench terrace for individual at Ropari huan Biate | 860 | 266 | 228760 | 228760 | 2206002003/IF/68894 | 304 | 2 | 1 | VEC
22 | CHALRANG | 10 | 79 | Constn of dug out pond for individual at Lalrintluanga huan chalrang | 790 | 266 | 210140 | 210140 | 2206002004/IF/68897 | 20 | 10 | 1 | VEC
|  | 10 | 78 | Constn of level bench terrace for individual at Thanzingi huan chalrang | 780 | 266 | 207480 | 207480 | 2206002004/IF/68901 | 500 | 2 | 1 | VEC
23 | CHAWNGTLAI | 10 | 97 | Constn.of Upland bench terrace for individual for Sanghlunkima huan chawngtlai | 970 | 266 | 258020 | 258020 | 2206002005/IF/68904 | 346 | 2 | 1 | VEC
|  | 10 | 98 | Constn.of Upland bench terrace for individual for Lalchawimawia huan chawngtlai | 980 | 266 | 260680 | 260680 | 2206002005/IF/68907 | 346 | 2 | 1 | VEC
|  | 10 | 98 | Constn.of Halfmoon level bench terrace for individual forLalchhanmawii huan chawngtlai | 980 | 266 | 260680 | 260680 | 2206002005/IF/68911 | 350 | 2 | 1 | VEC
|  | 10 | 98 | Constn.of Halfmoon level bench terrace for individual for Lalrampari huan chawngtlai | 980 | 266 | 260680 | 260680 | 2206002005/IF/68913 | 350 | 2 | 1 | VEC
24 | HMUNCHENG | 10 | 92 | Constn.of Afforestation At khawzawl kawng | 920 | 266 | 244720 | 244720 | 2206002009/DP/8788 | 200 nos. |  |  | VEC
25 | KHAWHAI | 10 | 200 | Development of land for community at Mualkhang zau 84 families khawhai | 2000 | 266 | 532000 | 532000 | 2206002012/LD/30809 | 100 | 28 | 1 | VEC
|  | 10 | 69 | Constn of Dug out pond for Saihlupuii huan khawhai | 690 | 266 | 183540 | 183540 | 2206002012/IF/68926 | 26 | 13 | 1.5 | VEC
|  | 10 | 68 | Constn of level bench terrace for individual at Zodinpuii huan khawhai | 680 | 266 | 180880 | 180880 | 2206002012/IF/68929 | 243 | 2 | 1 | VEC
|  | 10 | 69 | Constn of level bench terrace for individual at Johana huan khawhai | 690 | 266 | 183540 | 183540 | 2206002012/IF/68934 | 243 | 2 | 1 | VEC
|  | 10 | 69 | Constn of level bench terrace for individual at Neihchhungi huan jc.no-709 new | 690 | 266 | 183540 | 183540 | 2206002012/IF/68938 | 243 | 2 | 1 | VEC
|  | 10 | 69 | Constn of level bench terrace for individual at Lalhminghlua huan khawhai | 690 | 266 | 183540 | 183540 | 2206002012/IF/68942 | 243 | 2 | 1 | VEC
26 | KHAWZAWL-I | 10 | 50 | Constn.of Halfmoon level bench terrace for individual at JK.Malsawmzuali huan Kzl-I | 500 | 266 | 133000 | 133000 | 2206002013/IF/68944 | 178 | 2 | 1 | VEC
|  | 10 | 50 | Constn.of Halfmoon level bench terrace for individual at Biakzuali huan Kzl-I | 500 | 266 | 133000 | 133000 | 2206002013/IF/68946 | 178 | 2 | 1 | VEC
|  | 10 | 152 | Drainage of community water logged land from Haukhuma in to Sawrkarliana in (on Going) | 1520 | 266 | 404320 | 404320 | 2206002013/IC/3373 | 300 | 0.5 | 0.5 | VEC
27 | KHAWZAWL-II | 10 | 150 | Road side line plantation of forestry trees for community at NH-06 in Convergence with EF&CC kzl-II | 1500 | 266 | 399000 | 399000 | 2206002014/DP/8790 | 500 nos. |  |  | VEC
|  | 10 | 50 | Constn of Level bench terrace for individual at Lalhlimpuia huan kzl-II | 500 | 266 | 133000 | 133000 | 2206002014/IF/68952 | 178 | 2 | 1 | VEC
|  | 10 | 100 | Drainage of water logged -land for Community near MS - II New. | 1000 | 266 | 266000 | 266000 | 2206002014/IC/3374 | 170 | 0.5 | 0.5 | VEC
|  | 10 | 60 | Construction of Contour Trench for individual for JH Lalsangpuii | 600 | 266 | 159600 | 159600 | 2206002014/IF/68954 | 1700 nos. |  |  | VEC
|  | 10 | 50 | Wasteland Plantation of Horticulture trees for individual at Laldinliana Colney huan New | 500 | 266 | 133000 | 133000 | 2206002014/IF/68958 | 715 nos. |  |  | VEC
|  | 10 | 70 | Leveling/ shaping of wasteland for individual at lalngaihzuali | 700 | 266 | 186200 | 186200 | 2206002014/IF/68959 | 100 | 5 | 1 | VEC
|  | 10 | 62 | Constn. Of Stagerred trench for individual at Lalrinchhani pautu, | 620 | 266 | 164920 | 164920 | 2206002014/IF/68960 | 221 | 2 | 1 | VEC
|  | 10 | 50 | Constn of Dugout pond for Individuals at H Vanneihthanga huan New | 500 | 266 | 133000 | 133000 | 2206002014/IF/68964 | 20 | 12 | 1.5 | VEC
28 | TLANGMAWI | 10 | 42 | Constn.of level bench terrace for Biaktluanga huan new | 420 | 266 | 111720 | 111720 | 2206002014/IF/68967 | 150 | 2 | 1 | VEC
29 | TLANGPUI | 10 | 169 | Constn of dugout pond at Vanlalchhawna huan tlangpui | 1690 | 266 | 449540 | 449540 | 2206002030/IF/68975 | 50 | 20 | 2.4 | VEC
30 | LUNGTAN | 10 | 63 | Levelling/shaping of wasteland at Lalsailova J/C No -186 | 630 | 266 | 167580 | 167580 | 2206002019/IF/68979 | 180 | 5 | 1 | VEC
|  | 10 | 63 | Constn.of upland bench terrace for individual at PC. Biakdawla | 630 | 266 | 167580 | 167580 | 2206002019/IF/68981 | 220 | 2 | 1 | VEC
31 | NGAIZAWL | 10 | 95 | Constn of Dug Out pond for individual at Kham Khaw Tuang huan new | 950 | 266 | 252700 | 252700 | 2206002022/IF/68984 | 22.6 | 15 | 2 | VEC
|  | 10 | 95 | Constn of Dug Out pond for individual at Man Sian Lun huan new | 950 | 266 | 252700 | 252700 | 2206002022/IF/68987 | 22.6 | 15 | 2 | VEC
32 | N.CHALRANG | 10 | 59 | Constn.of level bench terrace for individual at Lalhrilliana huan n.chalrang | 590 | 266 | 156940 | 156940 | 2206002024/IF/68990 | 210 | 2 | 1 | VEC
|  | 10 | 42 | Constn.of level bench terrace for individual a Lalbanthanga huan n.chalrang | 420 | 266 | 111720 | 111720 | 2206002024/IF/68993 | 150 | 2 | 1 | VEC
|  | 10 | 41 | Constn.of level bench terrace for individual a R.Lalhmangaiha huan n.chalrang | 410 | 266 | 109060 | 109060 | 2206002024/IF/68995 | 146 | 2 | 1 | VEC
33 | RIANGTLEI | 10 | 88 | Drainage of water logged land for community at from Lungdawh kawn to Lalengmawia house | 880 | 266 | 234080 | 234080 | 2206002028/IC/3377 | 60 | 0.5 | 0.5 | VEC
34 | SIALHAWK | 10 | 50 | Constn.of Dugout pond for individual R.Lallungmuanpuia huan sialhawk | 500 | 266 | 133000 | 133000 | 2206002029/IF/68997 | 18 | 14 | 1.8 | VEC
|  | 10 | 50 | Constn.of Dugout pond for individual Zathanga huan sialhawk | 500 | 266 | 133000 | 133000 | 2206002029/IF/68998 | 18 | 14 | 1.8 | VEC
|  | 10 | 190 | Drainage of Water logged for Community near F.vanlalruata house sialhawk | 1900 | 266 | 505400 | 505400 | 2206002029/IC/3378 | 535 | 0.5 | 0.5 | VEC
|  | 10 | 194 | Drainage of Water logged for Community near Bus stand | 1940 | 266 | 516040 | 516040 | 2206002029/IC/3390 | 350 | 0.5 | 0.5 | VEC
35 | TUALTE | 10 | 95 | Along the coast of afforestation using forestries for community at Tualte hmun | 950 | 266 | 252700 | 252700 | 2206002033/DP/8819 | 577 nos. |  |  | VEC
|  | 10 | 155 | Constn of commmunity water logged land at Chalmawia in to C Thangzuala in. | 1550 | 266 | 412300 | 412300 | 2206002033/IC/3391 | 282 | 1 | 1 | VEC
36 | VANGTLANG | 10 | 99 | Road side line plantation of forestry trees for community from Eco - park to kawnpui vangtlang | 990 | 266 | 263340 | 263340 | 2206002036/DP/8820 | 750 nos. |  |  | VEC
37 | KHAWZAWL HERMON | 10 | 112 | Roadside tree plantation at chhumliamkawn to haidai champhai road hermon | 1120 | 266 | 297920 | 297920 | 2206002038/DP/8822 | 840 nos. |  |  | VEC
|  | 10 | 56 | Constn.of level bench terrace for Lalchhuanthangi huan new | 560 | 266 | 148960 | 148960 | 2206002038/IF/69099 | 510 | 2 | 1 | VEC
|  | 10 | 180 | Drainage of community water -Logged land for community from Lalremthanga in to Maunel ram | 1800 | 266 | 478800 | 478800 | 2206002038/IC/3392 | 102 | 1 | 1 | VEC
38 | KHAWZAWL KAWNZAR | 10 | 63 | constn of contour trench at Tuilakhnar kawnzar | 630 | 266 | 167580 | 167580 | 2206002039/IF/69100 | 450 nos. |  |  | VEC
|  | 10 | 126 | Drainage of community water logged land from Nunziri house to tuikhur kawnzar | 1260 | 266 | 335160 | 335160 | 2206002039/IC/3393 | 350 | 0.5 | 0.5 | VEC
|  |  | 8595 | G.TOTAL |  |  |  | 22862700
(TIMOTHY R.LALHMANGAIHA)
Programme Officer
Mahatma Gandhi National Rural Employment Guarantee Act
Khawzawl R.D. Block
Khawzawl.