## Sheet1
WORK ORDER FOR PROVIDING EMPLOYMENT TO THOSE HOUSE HOLDS ISSUED JOB CARDS WHO ARE DEMANDING EMPLOYMENT UNDER MGNREGA IN MIZORAM (JANUARY, 2024)
NAME OF DISTRICT |  |  | : | KHAWZAWL |  |  |  |  | Financial Year : 2023 - 2024
NAME OF BLOCK |  |  | : | KHAWZAWL | Work Start Date 22.1.2024: Work End Date : 4.2.2024
Sl. No. | Name of Village | No of work-ing days | No of Regis-tered Family | Name of work (please specify work for unskilled, semi-skilled and skilled Labour) | Unskilled Labour | Rate per day (Rs) | Unskilled Amount (Rs) | TOTAL | Work Code | Measurement of work in metre per benificiary |  |  | Work execu-ting agency
[10 empty] | Length (in metre) | Breadth (in metre) | Height (in metre)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | AIDUZAWL | 14 | 74 | Maintenance of Cement Concreat road from Lalengmawii in to Khawlai tuikhur, Aiduzawl | 1036 | 249 | 257964 | 257964 | IF/GIS/46460 | 32 | 3 | 0.2 | VEC
2 | CHHAWRTUI | 14 | 63 | Constn. Of Mini percolation tank at K. Vanhnuna Huan. Jc. No. 210 | 882 | 249 | 219618 | 219618 | IF/GIS/46461 | 3 | 3 | 2 | VEC
|  | 14 | 63 | Constn. Of Mini percolation tank at K Sangzama huan | 882 | 249 | 219618 | 219618 | IF/GIS/46462 | 3 | 3 | 2 | VEC
|  | 14 | 63 | Constn. Of Dugout pond at Lalchhandami Huan Jc.no. 323 | 882 | 249 | 219618 | 219618 | IF/GIS/46463 | 3 | 3 | 2 | VEC
|  | 14 | 64 | Constn. Of Mini percolation tank at Biakliani Huan. Jc. No. 266 | 896 | 249 | 223104 | 223104 | IF/GIS/46464 | 3 | 3 | 2 | VEC
3 | DULTE | 14 | 57 | Constn.of Dug out pond at Lalngaihzuala huan jc no-41 | 798 | 249 | 198702 | 198702 | IF/GIS/46465 | 20 | 19 | 2 | VEC
|  | 14 | 58 | Constn.of Dug out pond at Hmangaihkima khiangte huan jc no-316 | 812 | 249 | 202188 | 202188 | IF/GIS/46466 | 20 | 19 | 2 | VEC
|  | 14 | 58 | Constn.of Dug out pond at Lalchhuanvawra huan jc no-312 | 812 | 249 | 202188 | 202188 | IF/GIS/46467 | 20 | 19 | 2 | VEC
|  | 14 | 58 | Constn of Piggery Shelter at Khawsiami | 812 | 249 | 202188 | 202188 | IF/GIS/46468 | 5 | 3 | 2 | VEC
4 | KAWLKULH | 14 | 60 | Constn of Individual Farmpond Lalhmingmawia | 840 | 249 | 209160 | 209160 | IF/GIS/46469 | 3.5 | 3.5 | 1.5 | VEC
|  | 14 | 468 | Construction of Compost pit for 25 Families | 6552 | 249 | 1631448 | 1631448 | IF/GIS/46470 | 1.8 | 1.5 | 1.5 | VEC
5 | KHAWZAWL-III | 14 | 50 | Constn of Half Moon Terrace at Raldosanga huan.JC.No-686. | 700 | 249 | 174300 | 174300 | IF/GIS/46471 | 200 nos. |  |  | VEC
|  | 14 | 75 | Constn of Water Harvesting Tank at C.Vanlalena huan. JC.No-639. | 1050 | 249 | 261450 | 261450 | IF/GIS/46472 | 3.2 | 3 | 2 | VEC
|  | 14 | 74 | Constn of Contour Trench at R.Thanmawia huan. JC.No-537. | 1036 | 249 | 257964 | 257964 | IF/GIS/46473 | 200 nos. |  |  | VEC
|  | 14 | 75 | Constn of Farmpond TBC Lalrinawma huan | 1050 | 249 | 261450 | 261450 | IF/GIS/46474 | 25 | 20 | 2 | VEC
6 | KHAWZAWL-IV | 14 | 50 | Constn .of terrace at Lalnghinglova huan kawntengek.jc no-396 | 700 | 249 | 174300 | 174300 | IF/GIS/46475 | 650 | 2 | 1 | VEC
|  | 14 | 51 | Constn .of terrace at K.Lalrinmawia huan Jc.no-962 | 714 | 249 | 177786 | 177786 | IF/GIS/46476 | 650 | 2 | 1 | VEC
|  | 14 | 65 | Constn.of Individual farmpond at Lalzikpuii huan IR hnuai.jc no-448 | 910 | 249 | 226590 | 226590 | IF/GIS/46477 | 3.5 | 3 | 1.8 | VEC
|  | 14 | 65 | Constn.of farmpond Lalremruati huan bawng farm kawng.jc no-848 | 910 | 249 | 226590 | 226590 | IF/GIS/46478 | 3.5 | 3 | 1.8 | VEC
|  | 14 | 65 | Maintenance of Dugout pond at Vanlalzawna huan | 910 | 249 | 226590 | 226590 | IF/GIS/46479 | 21 | 20 | 2 | VEC
7 | KHAWZAWL-V | 14 | 79 | Construction of Dugout pond for K. Kapliana | 1106 | 249 | 275394 | 275394 | IF/GIS/46480 | 25 | 20 | 2 | VEC
|  | 14 | 80 | Construction of Dugout pond for Lalawmpuii | 1120 | 249 | 278880 | 278880 | IF/GIS/46481 | 25 | 20 | 2 | VEC
|  | 14 | 80 | Construction of Dugout pond for Lalnunpuia | 1120 | 249 | 278880 | 278880 | IF/GIS/46482 | 25 | 20 | 2 | VEC
|  | 14 | 80 | Construction of Dugout pond for Ngurliana Sailo | 1120 | 249 | 278880 | 278880 | IF/GIS/46483 | 25 | 20 | 2 | VEC
8 | KHUALEN | 14 | 53 | Renovation of Playfield (New) | 742 | 249 | 184758 | 184758 | IF/GIS/46484 | 20 | 17 | 2 | VEC
9 | NEIHDAWN | 14 | 29 | Constn of terrace at K. Lalrintluanga | 406 | 249 | 101094 | 101094 | IF/GIS/46485 | 400 | 2 | 1 | VEC
|  | 14 | 30 | Constn of terrace at Sangpuia | 420 | 249 | 104580 | 104580 | IF/GIS/46486 | 400 | 2 | 1 | VEC
|  | 14 | 30 | Constn of terrace at Liannghaka | 420 | 249 | 104580 | 104580 | IF/GIS/46487 | 400 | 2 | 1 | VEC
|  | 14 | 30 | Constn of terrace at PC Lalrinenga | 420 | 249 | 104580 | 104580 | IF/GIS/46488 | 400 | 2 | 1 | VEC
|  | 14 | 30 | Constn of terrace at Kapenga huan | 420 | 249 | 104580 | 104580 | IF/GIS/46489 | 400 | 2 | 1 | VEC
10 | PAMCHUNG | 14 | 84 | Constn of Dugout pond for Lalzamluaia (New) | 1176 | 249 | 292824 | 292824 | IF/GIS/46490 | 25 | 22 | 2 | VEC
11 | PUILO | 14 | 57 | Constn of Poultry Livestock shelter for K. Vanlalvena | 798 | 249 | 198702 | 198702 | IF/GIS/46491 | 5 | 3 | 2 | VEC
|  | 14 | 58 | Constn of Poultry Livestock shelter for C. Kapsanga | 812 | 249 | 202188 | 202188 | IF/GIS/46492 | 5 | 3 | 2 | VEC
12 | RABUNG | 14 | 75 | Constn of Dugout Pond at Rothanga J/C no 217 | 1050 | 249 | 261450 | 261450 | IF/GIS/46493 | 24 | 20 | 2 | VEC
|  | 14 | 43 | Constn of Level bench Terrace for Malsawma (New) | 602 | 249 | 149898 | 149898 | IF/GIS/46494 | 300 | 2 | 1 | VEC
|  | 14 | 75 | Constn of Farmpond at Chhuanawma J/C no 245 | 1050 | 249 | 261450 | 261450 | IF/GIS/46495 | 3 | 3 | 1.8 | VEC
|  | 14 | 75 | Constn of Irrigation Canal at Ramenga (New) | 1050 | 249 | 261450 | 261450 | IF/GIS/46496 | 190 | 1 | 1 | VEC
|  | 14 | 75 | Constn of Irrigation Canal at K. Laldawngliana(New) | 1050 | 249 | 261450 | 261450 | IF/GIS/46497 | 190 | 1 | 1 | VEC
13 | TUALPUI | 14 | 75 | Constn of Individual Water tank at HD Remthuama | 1050 | 249 | 261450 | 261450 | IF/GIS/46499 | 4 | 3 | 1.6 | VEC
|  | 14 | 76 | Constn of Individual Water tank at Israel Roluahpuia | 1064 | 249 | 264936 | 264936 | IF/GIS/46500 | 4 | 3 | 1.6 | VEC
14 | VANKAL | 14 | 52 | Constn of individual farmpond for K.lalluahthanga at Bellei.JC No-65 | 728 | 249 | 181272 | 181272 | IF/GIS/46502 | 3 | 2.5 | 1.8 | VEC
|  | 14 | 53 | Constn of water harvesting tank at Ramengi huan,khawhnuai zau JC No-125 | 742 | 249 | 184758 | 184758 | IF/GIS/46505 | 3 | 2.5 | 1.8 | VEC
15 | KHAWZAWL LUNGVAR | 14 | 63 | Constn of dugout pond for Lalzikpuii JC No-48 | 882 | 249 | 219618 | 219618 | IF/GIS/46509 | 20.5 | 20 | 2 | VEC
|  | 14 | 64 | Constn of land levelling for Lalbiakthuama JC No-9 | 896 | 249 | 223104 | 223104 | IF/GIS/46516 | 830 | 2 | 1 | VEC
|  | 14 | 50 | Constn of level bench terrace for Lalchakthanga JC No-53 | 700 | 249 | 174300 | 174300 | IF/GIS/46523 | 650 | 2 | 1 | VEC
16 | KAWLKULH NORTH | 14 | 64 | Constn. Of terrace at Singremmawia J/C No. 2206002042/48 | 896 | 249 | 223104 | 223104 | IF/GIS/46530 | 820 | 2 | 1 | VEC
|  | 14 | 200 | Compospit for 11 families | 2800 | 249 | 697200 | 697200 | IF/GIS/46535 | 1.8 | 1.5 | 1.5 | VEC
17 | VANCHENGPUI | 14 | 90 | Constn of WRC at Lalthanthuami J/C no 82 | 1260 | 249 | 313740 | 313740 | IF/GIS/46545 | 238 | 10 | 0.5 | VEC
|  | 14 | 90 | Constn of WRC at Lalhmuaka J/C no 83 | 1260 | 249 | 313740 | 313740 | IF/GIS/46546 | 238 | 10 | 0.5 | VEC
18 | KHAWZAWL ARRO | 14 | 68 | Constn of Dugout pond at Hmingthankhuma Huan (91) | 952 | 249 | 237048 | 237048 | IF/GIS/46572 | 22 | 20 | 2 | VEC
|  | 14 | 50 | Constn of Contour Trench at Zosanga Huan (69) | 700 | 249 | 174300 | 174300 | IF/GIS/46575 | 320 nos |  |  | VEC
19 | KHAWZAWL ZAINGEN | 14 | 262 | Land development at Zaingen hmunhlui for 22 families Phase -II | 3668 | 249 | 913332 | 913332 | IF/GIS/46577 | 3 ha |  |  | VEC
20 | ARRO | 14 | 49 | Constn Level Bench Terrace for individual at Lalneihkaii huan. JC.No.-36 | 686 | 249 | 170814 | 170814 | IF/GIS/46579 | 200 | 2 | 1 | VEC
21 | BIATE | 14 | 105 | Levelling/shaping of wasteland for H Lalnunmawia. Jc.No-254 | 1470 | 249 | 366030 | 366030 | IF/GIS/46581 | 400 | 5 | 1 | VEC
|  | 14 | 105 | Levelling/shaping of wasteland for Thanzuali Jc.No-567 | 1470 | 249 | 366030 | 366030 | IF/GIS/46582 | 400 | 5 | 1 | VEC
|  | 14 | 105 | Levelling/shaping of wasteland for Lalparliana. Jc.No-388 | 1470 | 249 | 366030 | 366030 | IF/GIS/46583 | 400 | 5 | 1 | VEC
|  | 14 | 105 | Levelling/shaping of wasteland for H Lalthianghlima. Jc.No-70 | 1470 | 249 | 366030 | 366030 | IF/GIS/46584 | 400 | 5 | 1 | VEC
|  | 14 | 106 | Construction of Dugout Pond for H Lawmsangpuii.Jc.No-801 | 1484 | 249 | 369516 | 369516 | IF/GIS/46586 | 25 | 10 | 1.5 | VEC
22 | CHALRANG | 14 | 82 | Constn.of Individual Farmpond at R.Vanlalhmuaka huan | 1148 | 249 | 285852 | 285852 | IF/GIS/46587 | 4 | 2 | 1 | VEC
|  | 14 | 82 | Constn.of Individual Farmpond at Lalruatkima huan | 1148 | 249 | 285852 | 285852 | IF/GIS/46588 | 4 | 2 | 1 | VEC
23 | CHAWNGTLAI | 14 | 90 | Levelling/shaping of wasteland at PC Malsawmtluanga huan.MZ-06-002-005-001/187 | 1260 | 249 | 313740 | 313740 | IF/GIS/46590 | 360 | 5 | 1 | VEC
|  | 14 | 90 | Levelling/shaping of wasteland at C. Lalhmangaiha huan.MZ-06-002-005-001/22 | 1260 | 249 | 313740 | 313740 | IF/GIS/46592 | 360 | 5 | 1 | VEC
|  | 14 | 90 | Levelling/shaping of wasteland at R. Rohlupuia huan.MZ-06-002-005-001/267 | 1260 | 249 | 313740 | 313740 | IF/GIS/46593 | 360 | 5 | 1 | VEC
|  | 14 | 82 | Constn.of Dug Out Pond for P. Ramsiama.MZ-06-002-005-001/297 | 1148 | 249 | 285852 | 285852 | IF/GIS/46596 | 20 | 10 | 1 | VEC
|  | 14 | 51 | Compost pit for 3 families | 714 | 249 | 177786 | 177786 | IF/GIS/46598 | 1.5 | 1.5 | 1.5 | VEC
24 | HMUNCHENG | 14 | 95 | Compost pit for 8 families | 1330 | 249 | 331170 | 331170 | IF/GIS/46599 | 1.5 | 1.5 | 1.5 | VEC
25 | KHAWHAI | 14 | 271 | Constn.of water courses for community for tawitawzawl zau | 3794 | 249 | 944706 | 944706 | IF/GIS/46600 | 450 | 0.5 | 0.5 | VEC
|  | 14 | 272 | Constn.of water courses for community at tuibel zau | 3808 | 249 | 948192 | 948192 | IF/GIS/46601 | 460 | 0.5 | 0.5 | VEC
26 | KHAWZAWL - I | 14 | 40 | Constn.of Level bench terrace for individual at Chawiliana huan. JC.No-680. | 560 | 249 | 139440 | 139440 | IF/GIS/46605 | 200 | 2 | 1 | VEC
|  | 14 | 50 | Levelling/shaping of wasteland at manthuami huan. JC.No-697. | 700 | 249 | 174300 | 174300 | IF/GIS/46607 | 167 | 3 | 1 | VEC
|  | 14 | 40 | Constn.of Upland bench terrace for individual at C.Lalbiakliana huan. JC.No-659. | 560 | 249 | 139440 | 139440 | IF/GIS/46609 | 200 | 2 | 1 | VEC
|  | 14 | 40 | Constn.of Upland bench terrace for individual at Lalthanungi huan. JC.No-771. | 560 | 249 | 139440 | 139440 | IF/GIS/46610 | 200 | 2 | 1 | VEC
|  | 14 | 77 | Constn of individual farmpond at Thangpuii huan. JC.No-821. | 1078 | 249 | 268422 | 268422 | IF/GIS/46612 | 4 | 2 | 1.5 | VEC
27 | KHAWZAWL - II | 14 | 85 | Constn of Mini Percolation tank for Community at artlangpeng. | 1190 | 249 | 296310 | 296310 | IF/GIS/46604 | 4 | 3 | 2 | VEC
|  | 14 | 100 | Constn of Minor Canal for Community at Lalhriatpuii huan | 1400 | 249 | 348600 | 348600 | IF/GIS/46610 | 120 | 0.5 | 0.5 | VEC
|  | 14 | 95 | Constn of Minor Canal for Community at Malsawmtluanga huan | 1330 | 249 | 331170 | 331170 | IF/GIS/46616 | 120 | 0.5 | 0.5 | VEC
|  | 14 | 85 | Wasteland block palatation of Horticulture Trees for individual at Lalnuntawma JC.No-1200 huan | 1190 | 249 | 296310 | 296310 | IF/GIS/46620 | 1 ha |  |  | VEC
|  | 14 | 60 | Development of fallow land for individual at LH Lalthazuala JC.No-822 huan | 840 | 249 | 209160 | 209160 | IF/GIS/46623 | 1 ha |  |  | VEC
|  | 14 | 85 | Constn of Mini Percolation Tank for Individual at Nurengi JC.No-92. | 1190 | 249 | 296310 | 296310 | IF/GIS/46605 | 4 | 3 | 2 | VEC
|  | 14 | 86 | Constn of Mini Percolation Tank for Individual at Ramnunsangi JC.No-87. | 1204 | 249 | 299796 | 299796 | IF/GIS/46608 | 4 | 3 | 2 | VEC
28 | TLANGMAWI | 14 | 43 | Constn. Of Dug out pond at Aichhungi huan Jc.No-18 | 602 | 249 | 149898 | 149898 | IF/GIS/46601 | 10 | 5 | 1 | VEC
29 | TLANGPUI | 14 | 84 | Levelling/shaping of wasteland at PC. Sangzuala huan Jc.No-227 | 1176 | 249 | 292824 | 292824 | IF/GIS/46595 | 100 | 6 | 1 | VEC
|  | 14 | 85 | Renovation of Public Pipeline | 1190 | 249 | 296310 | 296310 | IF/GIS/46597 | 300 |  |  | VEC
30 | LUNGTAN | 14 | 44 | Constn.of halfmoon terrace for individual Lalthantluanga huan | 616 | 249 | 153384 | 153384 | IF/GIS/46589 | 120 | 1 | 1 | VEC
|  | 14 | 44 | Constn.of halfmoon terrace for individual PC.Biakdawla huan | 616 | 249 | 153384 | 153384 | IF/GIS/46590 | 120 | 1 | 1 | VEC
|  | 14 | 44 | Constn.of halfmoon terrace for individual Laldinpuia huan | 616 | 249 | 153384 | 153384 | IF/GIS/46594 | 120 | 1 | 1 | VEC
31 | NGAIZAWL | 14 | 199 | Const.of Community Land development for Lungtlanghing zau | 2786 | 249 | 693714 | 693714 | IF/GIS/46583 | 49 | 20 | 1 | VEC
32 | N.CHALRANG | 14 | 72 | Levelling/shaping of wasteland at Lalruatkima huan JC No-193 | 1008 | 249 | 250992 | 250992 | IF/GIS/46578 | 100 | 7 | 1 | VEC
|  | 14 | 72 | Levelling/shaping of wasteland at Zaihlupuii huan JC No-141 | 1008 | 249 | 250992 | 250992 | IF/GIS/46580 | 100 | 7 | 1 | VEC
33 | RIANGTLEI | 14 | 100 | Drainage of water logged land from K.Romana House to Challawmi House | 1400 | 249 | 348600 | 348600 | IF/GIS/46576 | 100 | 0.4 | 0.4 | VEC
34 | SIALHAWK | 14 | 63 | Constn.of Individual farmpond at H.Lalruata huan jc.no-119 | 882 | 249 | 219618 | 219618 | IF/GIS/46557 | 3.5 | 2 | 1 | VEC
|  | 14 | 63 | Constn.of Individual farmpond at Laltanpuii huan jc.no-223 | 882 | 249 | 219618 | 219618 | IF/GIS/46562 | 3.5 | 2 | 1 | VEC
|  | 14 | 63 | Constn.of Individual farmpond at Lalparmawii huan jc no-670 new | 882 | 249 | 219618 | 219618 | IF/GIS/46568 | 3.5 | 2 | 1 | VEC
|  | 14 | 63 | Constn.of Individual farmpond at Chawngsiama huan jc no-30 new | 882 | 249 | 219618 | 219618 | IF/GIS/46569 | 3.5 | 2 | 1 | VEC
|  | 14 | 64 | Constn.of Dugout pond at Zothantluangi huan jc no-632 new | 896 | 249 | 223104 | 223104 | IF/GIS/46570 | 20 | 10 | 1 | VEC
|  | 14 | 64 | Constn.of water courses for community at Rinkimi huan Jc.no-214 | 896 | 249 | 223104 | 223104 | IF/GIS/46572 | 100 | 0.5 | 0.5 | VEC
|  | 14 | 64 | Constn.of water courses for community at C.Lalramnghaka huan Jc.no-479 | 896 | 249 | 223104 | 223104 | IF/GIS/46574 | 100 | 0.5 | 0.5 | VEC
|  | 14 | 64 | Constn.of Dugout pond at Ropuia huan jc no-66 new | 896 | 249 | 223104 | 223104 | IF/GIS/46571 | 20 | 10 | 1 | VEC
35 | TUALTE | 14 | 40 | Constn.of level bench terrace for individual for JH.Lalzemawia JC No-251 | 560 | 249 | 139440 | 139440 | IF/GIS/46542 | 150 | 2 | 1 | VEC
|  | 14 | 40 | Constn.of level bench terrace for individual for JH.Lalkhawngaiha JC No-147 | 560 | 249 | 139440 | 139440 | IF/GIS/46543 | 150 | 2 | 1 | VEC
|  | 14 | 50 | Constn of Dugout pond for Malsawmthanga JC No-10 | 700 | 249 | 174300 | 174300 | IF/GIS/46544 | 20 | 10 | 1 | VEC
|  | 14 | 60 | Constn of Individual farmpond for Lalchhuanmawia JC No-321 | 840 | 249 | 209160 | 209160 | IF/GIS/46548 | 3.5 | 2 | 1 | VEC
|  | 14 | 60 | Constn of Individual farmpond for Roluti JC No-242 | 840 | 249 | 209160 | 209160 | IF/GIS/46552 | 3.5 | 2 | 1 | VEC
36 | VANGTLANG | 14 | 103 | Constn. of community water harvesting ponds at High School Tlang. | 1442 | 249 | 359058 | 359058 | IF/GIS/46533 | 3 | 2 | 2 | VEC
37 | KHAWZAWL HERMON | 14 | 69 | Constn.of individual Farmpond for PC.Liankunga huan jc no-169 | 966 | 249 | 240534 | 240534 | IF/GIS/46506 | 4 | 2 | 1 | VEC
|  | 14 | 68 | Constn.of Piggery shelter for john Zamngaihpau huan jc no-99 | 952 | 249 | 237048 | 237048 | IF/GIS/46508 | 5 | 2.5 | 3 | VEC
|  | 14 | 68 | Constn.of Piggery shelter for john Lalzemawii huan jc no-447 | 952 | 249 | 237048 | 237048 | IF/GIS/46511 | 5 | 2.5 | 3 | VEC
|  | 14 | 68 | Constn.of Piggery shelter for john Lalzidinga huan jc no-33 | 952 | 249 | 237048 | 237048 | IF/GIS/46514 | 5 | 2.5 | 3 | VEC
|  | 14 | 69 | Constn.of individual Farmpond for Lalchhuankima huan jc no-84 | 966 | 249 | 240534 | 240534 | IF/GIS/46519 | 4 | 2 | 1 | VEC
38 | KHAWZAWL KAWNZAR | 14 | 65 | Constn. of Farm pond for Lalhruaitluanga huan Jc.No-109. | 910 | 249 | 226590 | 226590 | IF/GIS/46498 | 4 | 2 | 1 | VEC
|  | 14 | 64 | constn of Pit digging for Lalremzuala Nimbu huan Jc.No-59. | 896 | 249 | 223104 | 223104 | IF/GIS/46499 | 1 ha |  |  | VEC
|  | 14 | 64 | Constn of Pit digging of Thangdailova huan Jc.No-44. | 896 | 249 | 223104 | 223104 | IF/GIS/46502 | 1 ha |  |  | VEC
G.TOTAL |  |  | 8782 |  |  |  |  | 30614052
(LALTHAKIMA CHHANGTE)
Programme Officer
Mahatma Gandhi National Rural Employment Guarantee Act
Khawzawl R.D. Block
Khawzawl.